## Sayfa1
Activity | Start Month | End Month | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | 2027-03-01 | Apr 27 | 2027-05-01 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27 | Nov 27 | Dec 27 | Jan 28 | Feb 28
Project management & coordination | Sep 26 | Feb 28 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
Kick-off meeting & planning | Sep 26 | Oct 26 | ■ | ■
Needs analysis & learning outcomes | Sep 26 | Nov 26 | ■ | ■ | ■
Methodology design (mental resilience & match strategies) | Nov 26 | Apr 27 |  |  | ■ | ■ | ■ | ■ | ■ | ■
Educational video production (10 videos) | Dec 26 | 2027-05-01 |  |  |  | ■ | ■ | ■ | ■ | ■ | ■
Guidebook drafting & review | Dec 26 | Apr 27 |  |  |  | ■ | ■ | ■ | ■ | ■
Pilot trainings – Türkiye (tennis) | 2027-05-01 | Aug 27 | [8 empty] | ■ | ■ | ■ | ■
Pilot trainings – Ireland (padel) | 2027-05-01 | Aug 27 | [8 empty] | ■ | ■ | ■ | ■
Feedback collection & improvements | Jun 27 | Sep 27 | [9 empty] | ■ | ■ | ■ | ■
Online platform development & launch | Sep 27 | Dec 27 | [12 empty] | ■ | ■ | ■ | ■
Online workshops & dissemination | Sep 27 | Dec 27