## Gantt
Activity | Start | End | Sep26 | Oct26 | Nov26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28
Project management & coordination | Sep-26 | Feb-28
Kick-off meeting & planning | Sep-26 | Oct-26
Needs analysis & learning outcomes | Sep-26 | Nov-26
Methodology design (mental resilience & match strategies) | Oct-26 | Dec-26
Educational video production (10 videos) | Dec-26 | Mar-27
Guidebook drafting & review | Dec-26 | Apr-27
Pilot trainings – Türkiye (tennis) | May-27 | Jun-27
Pilot trainings – Ireland (padel) | May-27 | Jun-27
Feedback collection & improvements | Jun-27 | Sep-27
Online platform development & launch | Sep-27 | Dec-27
Dissemination & exploitation | Sep-27 | Feb-28